## Slide 1: PROGETTO ERASMUS+ KA220 DANCECARE
Dance Movement Therapy and Conscious Movement as innovative tools in emotional education and support for long-term caregivers.

## Slide 2: OVERVIEW
The development of DanceCARE educational program will contribute to a holistic approach to education and training in a lifelong learning perspective.
Cooperation partnership in Adult Education
HORIZONTAL PRIORITY: Inclusion and diversity in all fields of education, training, youth and sport
Additional priority:
Creating and promoting learning oportunities among all citizens and generations
Improving the availability of hight quality, flexible and recognised learning for adults

## Slide 3: DANCECARE CONCEPT
KEY CHALLENGE: PROVIDING SUPPORT FOR INFORMAL CAREGIVERS (EU LCT Report, 2021)
Both informal and formal care is demanding and LTC caregivers are often isolated and at risk psychological distress and depression.
Caregiver BURDEN is a specific form of stress that tends to become chronic the longer the caring situation lasts and manifests itself in the most diverse and subjective forms:
sleep problems, appetite problems, mood decline, attention and concentration difficulties, memory difficulties, irritability and anxiety, persistent worry, somatization symptoms, ease of falling ill.
LTC CAREGIVERS NEED FOR SUPPORT TO FACE BURDEN
EMBODIED COGNITION APPROACH
Scientific community has long discussed the need to put bodily processes at the center of education, care and mental health. It could be argued that there is no comprehensive intervention that does not also take the body into account. This concept is slowly spreading and DanceCARE represents a valuable step towards a paradigm shift, adopting mind-body methodologies.
NETWORKING
As literature shows that only the multi-component intervention category can significantly reduce the care load, self-help groups and chats intercept the need for networking, counteracting isolation.

## Slide 4: DANCECARE CONCEPT
A caregiver who takes care of him/herself,
who is aware of his/her limits and resources also on an emotional level,
who fits into a peer group and avoids isolation,
will be healthier,
will resort less to the use of drugs,
will turn less to the health care system;
and will also be able to care for his/her elderly person better.

## Slide 5: OUTLINE OF OBJECTIVES
GENERAL OBJETIVE To reduce the burden of formal and informal LTC caregivers, reducing the risk of depression and isolation
1. Reducing the burden of LTC informal and formal caregivers | 2. Reducing depression of LCT informal and formal caregivers | 3. Improving the quality of life in ageing and the way in which older people are cared for | 4. Reducing isolation and Promoting communication and networking between different types of LTC carers | 5. Systematize and field-test the effectiveness of the body-mind methodologies used | 6. Enhance and expand the DMT methodologies through the inclusion of the WM method | 7. Optimize the use of the DanceCARE educational program through digitization-BLENDED | 8. Disseminating the created educational program to various training institutions specialized in DMT | 9. Involve stakeholders in adopting the DanceCARE curriculum as an ongoing education tool

## Slide 6: TARGET GROUPS
DIRECT
INFORMAL CAREGIVERS who provide care for an elderly family member or person by choiche and/or necessity, without any kind of remineration
FORMAL CAREGIVERS who carry out care work in close contact with family members (e.g. live-in carers, family assistant, migrant care workers)
INDIRECT
OLDER PEOPLE with LTC needs
SOCIAL AND HEALTH CARE INSTITUTIONS
PROFESSIONAL DMT ASSOCIATIONS AND SCHOOLS

## Slide 7: PARTNERSHIP
COORDINATOR INRCA | National Public Body - Management, research expert and pilot site | Italy
UNIVERSITATE DE VALENCIA | Higher Education institution - Research expert and pilot site | Spain
AKTIOS | Small and medium sized enterprise - Pilot site partner and dissemination | Greece
EADMT (European Association of Dance Movement Therapy) | Non governamental organization - Metodology expert | Germany
Wise Motion Community (Doctor Hanna Poikonen) | Small and medium sized enterprise - Metodology expert | Finland
Computer Solution SA | Small and medium sized enterprise - Expert for technological part development | Greece

## Slide 8: FOCUS ON WP2 - PREPARATION AND DESIGN OF THE DANCECARE TRAINING PROGRAM
Flavia Galassi [content creator, metodology expert and trainer]
Sara Santini [Project Management and P.I.]

## Slide 9
WP1 Project Management
WP2 Preparation and design of the DanceCARE training program
Task 2.1 Online research on LTC caregivers needs
Task 2.2 DMT e WM expert consultation and recruitment
Task 2.3 Analysis and matching of the results
Task 2.4 Design of the whole DanceCARE curriculum
Task 2.5 Creation of ad hoc videos
Task 2.6 Dissemination and exploitation activities
WP3 Development of the DanceCARE platform and chat
Task 3.1 Creation of the DanceCARE platform and chat
Task 3.2 Focus groups with end-users
Task 3.3 Dissemination and exploitation activities
WP4 DanceCARE training activation - PILOT
Task 4.1 Recruitment of LTC caregivers
Task 4.2 DanceCARE pilot activation
Task 4.3 Self-help groups activation
Task 4.5 Dissemination and exploitation activities
WP5 Assesment of the DanceCARE impact and sharing of the results
Task 5.1 Collection, transcripion and analysis of pilot data
Task 5.2 Sharing of the results
Task 5.3 Dissemination and exploitation activities
D1.1QP + D1.2 Financial Guidelines |  |  |  |  |  |  |  |  |  |  |  | D1.3 Interim report |  |  |  |  |  |  |  |  |  |  |  |  |  |  | D1.4 Final Report |  | 
 |  | TM1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | D2.1 study design and guidelines for interviewers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | D2.2 guidelines for trainers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | D2.3 guidelines for making videos |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  | TM2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | TM3 |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ME | ME | ME |  | 

## Slide 10: TASK2.1 – ON-LINE SEARCH ON LTC CARERS NEEDS AND SOFT SKILLS TO BE DEVELOPED
TIME FRAME: from now to 15 march 2024
Responsible Partner: Aktios, Polibienestar + all
EXPECTED RESULT: identify 5 soft skills to be developed trough DanceCARE program and write a short report
+ Writing a Quality Plan (QP) to be shared in the Kick-off meeting (KOM)

## Slide 11: TASK2.2 – DMT AND WM EXPERTS CONSULTATION
TIME FRAME: from now to 30 april 2024
Responsible Partner: EADMT + national association and institutions
EXPECTED RESULTS: identify 6 DMT techniques that have proven to be the most effective in cases of stress and depression, trough consultation of DMT and WM experts all over Europe
SUB-TASKS:
Formulation of the ON-LINE QUESTIONNAIRE to be submitted to DMT experts (english version) [by 15 march]
Creation of google modules in Italian, Greek, Spanish (German and Finnish) [by 30 march]
Diffusion of the questionnaire trough DMT national associations and institutions [by 30 april]
Identify and recruit 3 DMT expert trainers for each pilot site [between 30 april and 15 june]

## Slide 12: TASK2.3 – ANALYSIS AND MATCHING OF THE RESULTS
TIME FRAME: from 30 april to 15 july 2024
Responsible partners: INRCA, Polibienestar
EXPECTED RESULT: Report on the results of the on-line consultation
+ D2.1. Writing the STUDY DESIGN and GUIDELINES FOR INTERVIEWERS
SUB-TASKS:
Create a dataset based on the questionnaire [by 30 april]
Analyse quantitative and qualitative data to identify the most usefull DMT techniques [by 15 june]
Write a Report to be used for setting DMT modules [by 30 june]
On-line focus group with DMT and WM experts (10) [by 10 july]

## Slide 13: TASK2.4 – DESIGN OF THE WHOLE DANCECARE CURRICULUM
TIME FRAME: from 15 july to15 november 2024
Responsible Partner: WM and EADMT + AKTIOS and all
EXPECTED RESULTS: creation of all the modules of the DanceCARE training program and GUIDELINES FOR TRAINERS (D2.2) and GUIDELINES FOR VIDEO MAKING(D2.3)
SUB-TASKS:
3 meetings between EADMT and WM for definition of 6-7 modules «Body-mind education for stress relief» [by 1° october]
2 meetings between Aktios, INRCA and Polibinestar for definition of 3-4 modules «How to do if» [by 1° october]
Setting and writing GUIDELINES FOR VIDEO-MAKING [by 1° october]
Setting and writing the GUIDELINES FOR TRAINERS [by 15 november]

## Slide 14: TASK2.5 – CREATION OF AD HOC VIDEOS
TIME FRAME: from 1° october to 31 december 2024
Responsible Partner: INRCA, WM, EADMT all + associated (PoliArte)
EXPECTED RESULTS: Creation of at least one ad hoc video per module
SUB-TASKS:
Involve all the trainers in the creation of videos, following the D2.2. and D2.3. guidelines [by 31 october]
Dub/subtitles the videos in the languages of the Partners involved [by 31 december]
Start to think about the most suitable platform to be used for DanceCARE program…

## Slide 15: TASK2.6 – DISSEMINATION AND EXPLOITATION ACTIVITIES
TIME FRAME: from now to 31 december 2024
Responsible Partner: Aktios, Computer Solution + all (associated partner: PoliArte)
SUB-TASKS:
Creation of a Logo, font and colors for DanceCARE project to be voted between all partners [by 30 april]
Setting a plan for dissemination: define ashtags to be used for the posts on social media, define timing and languages to be used, and other aspects connected to dissemination [by the KOM]
Creation of a web site, Facebook and LinkedIN pages for the project, where all partners can post their updates in the country's language to engage the community and raise awareness of LTC [by 15 june]